MANAGEMENT PLAN TO DEAL WITH THE ISSUING OF PRINCIPALS BULLETIN VOLUME 4 OF 2015 AND FILLING OF ADVERTISED POSTS

| PHASE | ACTION/ACTIVITY | TARGET DATES | RESPONSIBILITY |
| --- | --- | --- | --- |
| Phase 1 | Preparation |  |  |
| 1.1 | Verification of draft bulletin | 4 July 2015 | HRP |
| 1.2 | Submission of bulletin to SG | 14 July 2015 | HRA |
| 1.3 | Approval of bulletin | 17July 2015 | SG |
| 1.4 | Distribution of bulletin | 21 July 2015 | HRA |
| 1.5 | Closing date. | 28 August 2015 | ALL |
| 1.6 | Compilation of a Computer Master list of all eligible applicants. | 31 Augustus 2015 – 11 September 2015 | District Director/ EDO |
| 1.7 | Forward eligible applications with alphabetical master list to Institution SGB’s. |  |  |
| 1.8 | Support schools to implement Circular 49/2005. | Ongoing | District Director/ EDO |
| Phase 2 | CONSTITUTION OF PANELS, INVITATION OF ORGANIZED LABOUR, SHORTLISTING & INTERVIEWING PROCESS |  |  |
| 2.1 | Constitution of Shortlisting and Interviewing Panel. | 14 – 25 September 2015 | SGB/Panel/ EDO |
| 2.2 | Invitation to Observers from PELRC Unions. |  |  |
| 2.3 | Shortlisting. |  |  |
| 2.4 | Interview of Candidates. |  |  |
| Phase 3 | RECOMMENDATION AND SUBMISSION FOR APPROVAL OF APPOINTMENT |  |  |
| 3.1 | Interview Panel presents outcome to SGB for ratification of ranking. | 28 September 2015 – 9 October 2015 | Panel/ SGB/District Director/EDO |
| 3.2 | Rank recommended candidates and send documents together with completed Forms and minutes of interviews to Director HRA for approval of appointment of nominated candidate. |  |  |
| 3.3 | Successful applicant is given letter of offer of appointment. |  |  |
| 3.4 | Successful applicant is given 7 (seven) days to accept offer of appointment. |  |  |
| 3.5 | Successful applicant is given letter of appointment. |  |  |
| Phase 4 | ASSUMPTION OF DUTY |  |  |
| 4.1 | Successful applicant assumes duty. | 12 October 2015(w.e.f. 1 October 2015) | Distr. Dir. through EDO’s |
| 4.2 | Unsuccessful applicants to be notified by SGB of outcome of interview. | 12 October 2015 | EDO |
| Phase 5 | REPORTING |  |  |
| 5.1 | Report to Provincial Office: Human Resource Administration in respect of filling of vacancies. | Weekly | District Director |
| 5.2 | Report to SG in respect of filling of posts. | Monthly | HRA |